## Overview
TechEarnest CRM — Full Application Sprint Backlog (through V2)
Companion plan | docs/PRODUCT_OPTIMIZATION_AND_V2_DELIVERY_PLAN.md
Generated | 2026-09-22
How to use
1. Filter UserStories by Sprint or Status
2. Assign Owner; set Status as work progresses
3. Allowed Status values: Not Started ¦ In Progress ¦ Blocked ¦ Done ¦ Deferred
4. Do not delete Story IDs; add new rows at bottom if needed
Phase summary
P0 Platform Split | S1–S3 | Super Admin console; org create; Prospect Orgs; hide tenant Leads
P1 UX System | S4–S7 | Forms, RecordShell, advanced filters all live modules
P2 Metadata Studio | S8–S11 | ServiceNow-like tables/fields/forms/lists/CRUD ACL/FLS
P3 Depth | S12–S13 | Bulk, duplicates, meetings/calls, delivery UX
P4 Engines | S14–S15 | Approval + Workflow
P5 Finance | S16–S18 | Taxes, Invoices, Payments, Credit Notes
P6 Contracts/Expenses | S19–S20 | Contracts + Expenses
P7 Procurement | S21–S22 | Vendors + POs
P8 Reports | S23–S24 | Analytics + profitability
P9 Portal | S25–S26 | Customer portal + hardening
Product rules
Super Admin sells/manages organizations — does NOT run tenant CRM Leads
Organization Admin runs complete tenant CRM + V2 modules
Org Admin configures tables/forms/lists/CRUD via Metadata & ACL Studio (role-based)

## SprintCalendar
Sprint | Phase | Theme | Goal | Status
S1 | P0 | Platform Console | Layout + API gate + hide tenant CRM for Super Admin | Not Started
S2 | P0 | Organizations | Multi-org create/suspend/detail | Not Started
S3 | P0 | Prospect Orgs | SaaS sales pipeline + convert to org | Not Started
S4 | P1 | Form kit CRM | Shared form system + CRM forms | Not Started
S5 | P1 | Form kit Delivery | Projects/resources/timesheet forms | Not Started
S6 | P1 | Admin + RecordShell | Admin forms + RecordShell | Not Started
S7 | P1 | Advanced Filters | Filter catalogs every module | Not Started
S8 | P2 | Dictionary | Studio shell + Table/Field dictionary + seeds | Not Started
S9 | P2 | Form/List designers | Form + List + related layouts + policies | Not Started
S10 | P2 | Table ACL | CRUD matrix UI + server enforce + roles UX | Not Started
S11 | P2 | FLS + rollout | Field ACL + layouts on all modules | Not Started
S12 | P3 | CRM depth | Bulk, duplicates, meetings/calls | Not Started
S13 | P3 | Delivery depth | Project/allocation UX + related lists | Not Started
S14 | P4 | Approvals | Engine + timesheet + inbox | Not Started
S15 | P4 | Workflow | Outbox + Deal WON notify | Not Started
S16 | P5 | Finance foundation | Tax + invoice draft + billable pull | Not Started
S17 | P5 | Finance lifecycle | Issue/pay/overdue + filters | Not Started
S18 | P5 | Credit notes | Credits + invoice detail | Not Started
S19 | P6 | Contracts | CRUD + reminders + filters | Not Started
S20 | P6 | Expenses | CRUD + approval + filters | Not Started
S21 | P7 | Vendors/PO draft | Vendors + PO draft | Not Started
S22 | P7 | PO approval | Lifecycle + filters | Not Started
S23 | P8 | Reports core | Gallery + sales/project reports | Not Started
S24 | P8 | AR + Profit | Aging + profitability | Not Started
S25 | P9 | Portal auth/API | portal_users + read APIs | Not Started
S26 | P9 | Portal UI + UAT | UI + hardening + E2E UAT | Not Started

## UserStories
Story ID | Sprint | Phase | Epic | Module | Title | Description | Acceptance Criteria | Persona | Priority | Story Points | Status | Owner | Dependencies | Updated On | Notes
US-S1-001 | S1 | P0 Platform Split | Platform Console | Platform | Separate Platform Console layout for Super Admin | Super Admin lands on /platform with Platform nav; tenant CRM modules are hidden. | SUPER_ADMIN default home is Platform Dashboard; /leads not in Platform nav; tenant routes redirect or 403 unless explicitly designed support tool. | Super Admin | P0 | 8 | Done |  |  | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S1-002 | S1 | P0 Platform Split | Platform Console | Auth/RBAC | Enforce PLATFORM-only access on /api/v1/platform/** | All platform APIs require PLATFORM data scope and platform permissions. | Org-scoped users receive 403/404 on platform APIs; tests cover cross-access. | Super Admin | P0 | 5 | Done |  | US-S1-001 | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S1-003 | S1 | P0 Platform Split | Platform Console | Navigation | Tenant users never see Platform Console nav | Org Admin and below only see tenant modules. | No Platform links for ORGANIZATION/REGION/TEAM/OWN scopes. | Org Admin | P0 | 3 | Done |  |  | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S1-004 | S1 | P0 Platform Split | Platform Console | Dashboard | Platform dashboard KPIs (orgs, users, active orgs) | High-level SaaS health cards without exposing tenant PII. | Shows org count, active users (aggregate), suspended orgs; clutter-free cards. | Super Admin | P1 | 5 | Done |  | US-S1-001 | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S2-001 | S2 | P0 Platform Split | Organizations | Organizations | List organizations with search/filter/status | Platform Organizations module list with ModuleListShell pattern. | Filter by status/name; total records; no tenant CRM fields. | Super Admin | P0 | 5 | Done |  | US-S1-001 | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S2-002 | S2 | P0 Platform Split | Organizations | Organizations | Create organization wizard | Create org: name, slug, timezone, currency, primary admin invite/password, default region. | Creates org + default region + ORGANIZATION_ADMIN user; audit logged; Save works; validation clear. | Super Admin | P0 | 13 | Done |  | US-S2-001 | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S2-003 | S2 | P0 Platform Split | Organizations | Organizations | Activate / Suspend organization | Lifecycle controls; suspended org users cannot login. | Suspend blocks login with clear message; reactivate restores; audited. | Super Admin | P0 | 5 | Done |  | US-S2-001 | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S2-004 | S2 | P0 Platform Split | Organizations | Organizations | Organization detail RecordShell (platform) | Overview of org settings, admin contacts, usage counts. | Detail tabs Overview/Users summary/Audit; clutter-free. | Super Admin | P1 | 5 | Done |  |  | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S3-001 | S3 | P0 Platform Split | Prospect Orgs | Prospect Orgs | Prospect Organizations module (SaaS sales) | Track companies we sell TechEarnest CRM to — separate from tenant Leads. | CRUD prospect orgs; stages New→Qualified→Proposal→Won/Lost; Super Admin only; never writes tenant leads. | Super Admin | P0 | 13 | Done |  | US-S1-001 | 2026-09-22 | Batch 2 shipped
US-S3-002 | S3 | P0 Platform Split | Prospect Orgs | Prospect Orgs | Convert Won Prospect Org → Create Organization | From won prospect, launch org create wizard with prefill. | Prefills name; creates tenant org; links prospect to organization_id; audited. | Super Admin | P1 | 8 | Done |  | US-S3-001,US-S2-002 | 2026-09-22 | Batch 2 shipped
US-S3-003 | S3 | P0 Platform Split | Prospect Orgs | Prospect Orgs | Advanced filters for Prospect Orgs | Stage, owner, value range, created date, source. | FilterEngine whitelist; saved views private. | Super Admin | P1 | 5 | Done |  | US-S3-001 | 2026-09-22 | Batch 2 shipped
US-S3-004 | S3 | P0 Platform Split | Platform Console | Leads | Remove/hide tenant Leads from Super Admin UX | Ensure Super Admin does not manage tenant leads as SaaS ops work. | No default Leads menu; documentation updated; QA checklist signed. | Super Admin | P0 | 3 | Done |  | US-S1-001 | 2026-09-22 | Batch 2 shipped
US-S4-001 | S4 | P1 UX System | Form System | Leads | Optimize Lead create/edit form (sections + progressive disclosure) | Redesign Lead form: primary fields first, Additional details, Save/Save & New, unsaved guard, lookup filters. | ≤8 primary fields visible; validation inline; Cancel/Save/Save&New; region/owner defaults; mobile single column. | Org User | P0 | 5 | Done |  |  | 2026-09-22 | Batch 2 shipped
US-S4-002 | S4 | P1 UX System | Form System | Contacts | Optimize Contact create/edit form (sections + progressive disclosure) | Redesign Contact form: primary fields first, Additional details, Save/Save & New, unsaved guard, lookup filters. | ≤8 primary fields visible; validation inline; Cancel/Save/Save&New; region/owner defaults; mobile single column. | Org User | P0 | 5 | Not Started
US-S4-003 | S4 | P1 UX System | Form System | Accounts | Optimize Account create/edit form (sections + progressive disclosure) | Redesign Account form: primary fields first, Additional details, Save/Save & New, unsaved guard, lookup filters. | ≤8 primary fields visible; validation inline; Cancel/Save/Save&New; region/owner defaults; mobile single column. | Org User | P0 | 5 | Not Started
US-S4-004 | S4 | P1 UX System | Form System | Deals | Optimize Deal create/edit form (sections + progressive disclosure) | Redesign Deal form: primary fields first, Additional details, Save/Save & New, unsaved guard, lookup filters. | ≤8 primary fields visible; validation inline; Cancel/Save/Save&New; region/owner defaults; mobile single column. | Org User | P0 | 5 | Not Started
US-S4-005 | S4 | P1 UX System | Form System | Activities | Optimize Activity create/edit form (sections + progressive disclosure) | Redesign Activity form: primary fields first, Additional details, Save/Save & New, unsaved guard, lookup filters. | ≤8 primary fields visible; validation inline; Cancel/Save/Save&New; region/owner defaults; mobile single column. | Org User | P0 | 5 | Not Started
US-S4-006 | S4 | P1 UX System | Form System | Design System | Shared FormSection / FormActions / UnsavedGuard components | Reusable form kit used by all modules. | Documented usage; used by at least Leads+Accounts+Contacts. | Engineer | P0 | 8 | Not Started
US-S5-001 | S5 | P1 UX System | Form System | Projects | Optimize Project create/edit form | Apply form kit to Project with module-specific sections. | Same DoD as S4 forms; permissions respected; clutter-free. | Org User | P1 | 5 | Not Started
US-S5-002 | S5 | P1 UX System | Form System | Project Tasks | Optimize Project Task create/edit form | Apply form kit to Project Task with module-specific sections. | Same DoD as S4 forms; permissions respected; clutter-free. | Org User | P1 | 5 | Not Started
US-S5-003 | S5 | P1 UX System | Form System | Milestones | Optimize Milestone create/edit form | Apply form kit to Milestone with module-specific sections. | Same DoD as S4 forms; permissions respected; clutter-free. | Org User | P1 | 5 | Not Started
US-S5-004 | S5 | P1 UX System | Form System | Resources | Optimize Resource create/edit form | Apply form kit to Resource with module-specific sections. | Same DoD as S4 forms; permissions respected; clutter-free. | Org User | P1 | 5 | Not Started
US-S5-005 | S5 | P1 UX System | Form System | Allocations | Optimize Allocation create/edit form | Apply form kit to Allocation with module-specific sections. | Same DoD as S4 forms; permissions respected; clutter-free. | Org User | P1 | 5 | Not Started
US-S5-006 | S5 | P1 UX System | Form System | Skills | Optimize Skill create/edit form | Apply form kit to Skill with module-specific sections. | Same DoD as S4 forms; permissions respected; clutter-free. | Org User | P1 | 5 | Not Started
US-S5-007 | S5 | P1 UX System | Form System | Timesheets | Optimize Timesheet / Time Entry create/edit form | Apply form kit to Timesheet / Time Entry with module-specific sections. | Same DoD as S4 forms; permissions respected; clutter-free. | Org User | P1 | 5 | Not Started
US-S6-001 | S6 | P1 UX System | Form System | Users | Optimize User forms & list UX | Tenant admin User uses ModuleListShell + form kit. | Consistent with CRM lists; scoped by permissions. | Org Admin | P1 | 5 | Not Started
US-S6-002 | S6 | P1 UX System | Form System | Roles | Optimize Role forms & list UX | Tenant admin Role uses ModuleListShell + form kit. | Consistent with CRM lists; scoped by permissions. | Org Admin | P1 | 5 | Not Started
US-S6-003 | S6 | P1 UX System | Form System | Regions | Optimize Region forms & list UX | Tenant admin Region uses ModuleListShell + form kit. | Consistent with CRM lists; scoped by permissions. | Org Admin | P1 | 5 | Not Started
US-S6-004 | S6 | P1 UX System | Form System | Departments | Optimize Department forms & list UX | Tenant admin Department uses ModuleListShell + form kit. | Consistent with CRM lists; scoped by permissions. | Org Admin | P1 | 5 | Not Started
US-S6-005 | S6 | P1 UX System | Form System | Settings | Optimize Organization Settings forms & list UX | Tenant admin Organization Settings uses ModuleListShell + form kit. | Consistent with CRM lists; scoped by permissions. | Org Admin | P1 | 5 | Not Started
US-S6-006 | S6 | P1 UX System | RecordShell | Platform UI | RecordShell component (Overview/Related/Activities/Notes/Documents/Audit) | Reusable record detail architecture. | Adopted on Lead + Account + Deal; tabs permission-aware. | Org User | P0 | 13 | Not Started
US-S6-007 | S6 | P1 UX System | RecordShell | Audit Logs | Optimize Audit Logs list + filters | Filter by action, entity, user, date, region. | Advanced filters; no secrets in payload display. | Org Admin | P1 | 5 | Not Started
US-S7-001 | S7 | P1 UX System | Advanced Filters | Leads | Advanced filter catalog for Leads | Whitelist fields: status,source,priority,owner,region,value,created,unconverted. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-002 | S7 | P1 UX System | Advanced Filters | Contacts | Advanced filter catalog for Contacts | Whitelist fields: account,status,owner,email,designation. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-003 | S7 | P1 UX System | Advanced Filters | Accounts | Advanced filter catalog for Accounts | Whitelist fields: type,status,industry,region,hasOpenDeals. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-004 | S7 | P1 UX System | Advanced Filters | Deals | Advanced filter catalog for Deals | Whitelist fields: stage,value,closeDate,account,owner,aging. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-005 | S7 | P1 UX System | Advanced Filters | Activities | Advanced filter catalog for Activities | Whitelist fields: type,status,due,relatedType,assignee. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-006 | S7 | P1 UX System | Advanced Filters | Documents | Advanced filter catalog for Documents | Whitelist fields: entityType,visibility,uploadedBy,created. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-007 | S7 | P1 UX System | Advanced Filters | Projects | Advanced filter catalog for Projects | Whitelist fields: status,account,manager,dates,delayed. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-008 | S7 | P1 UX System | Advanced Filters | Project Tasks | Advanced filter catalog for Project Tasks | Whitelist fields: status,project,assignee,due,priority. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-009 | S7 | P1 UX System | Advanced Filters | Milestones | Advanced filter catalog for Milestones | Whitelist fields: project,status,due. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-010 | S7 | P1 UX System | Advanced Filters | Resources | Advanced filter catalog for Resources | Whitelist fields: status,region,skill,availability. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-011 | S7 | P1 UX System | Advanced Filters | Allocations | Advanced filter catalog for Allocations | Whitelist fields: project,resource,status,overlap. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-012 | S7 | P1 UX System | Advanced Filters | Skills | Advanced filter catalog for Skills | Whitelist fields: name,category. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S7-013 | S7 | P1 UX System | Advanced Filters | Timesheets | Advanced filter catalog for Timesheets | Whitelist fields: status,week,resource,billable. Nested AND/OR where engine supports; saved views. | Filter rail works; invalid fields rejected server-side; Current User/Region operators where applicable. | Org User | P0 | 5 | Not Started
US-S8-001 | S8 | P2 Metadata Studio | Metadata Studio | Studio | Metadata & ACL Studio shell (Org Admin) | Clutter-free Studio at /admin/studio: table navigator, canvas, property inspector, Preview/Publish. | Org Admin only; Super Admin does not use for tenant CRM; nav entry under Admin; empty states. | Org Admin | P0 | 13 | Not Started
US-S8-002 | S8 | P2 Metadata Studio | Metadata Studio | Dictionary | Table Dictionary: register all business modules as tables | sys_table (or equivalent): code, label, plural, active, module group; seed all CRM/delivery/admin tables. | API list/get; Studio Tables view; cannot delete system tables; org-scoped overrides supported. | Org Admin | P0 | 13 | Not Started |  | US-S8-001
US-S8-003 | S8 | P2 Metadata Studio | Metadata Studio | Dictionary | Field Dictionary: system fields + custom field types | sys_field: type, label, help, mandatory, default, reference, active, system flag; custom fields storage decision implemented. | Add/edit/deactivate custom field; system fields editable for label/help only; max custom fields enforced; audited. | Org Admin | P0 | 13 | Not Started |  | US-S8-002
US-S8-004 | S8 | P2 Metadata Studio | Metadata Studio | Dictionary | Seed Field Dictionary for Leads, Contacts, Accounts, Deals, Activities | Import current schema into dictionary so Studio reflects live modules. | All primary fields listed; types match DB; Studio browse works without manual entry. | Engineer | P0 | 8 | Not Started |  | US-S8-003
US-S8-005 | S8 | P2 Metadata Studio | Metadata Studio | Permissions | Studio permissions METADATA_VIEW / METADATA_MANAGE | Gate Studio APIs and UI; default grant to ORGANIZATION_ADMIN. | Non-admin 403; ROLE_MANAGE alone insufficient unless seeded; tests. | Org Admin | P0 | 5 | Not Started |  | US-S8-001
US-S9-001 | S9 | P2 Metadata Studio | Form Designer | Studio | Form Layout Designer (sections, order, progressive disclosure) | Drag fields into sections; mark primary vs Additional details; create vs edit layouts. | Publish updates effective layout; discard draft; Preview; no scripts required. | Org Admin | P0 | 13 | Not Started |  | US-S8-003
US-S9-002 | S9 | P2 Metadata Studio | Form Designer | Platform UI | Runtime DynamicForm reads published form layout | Form kit renders from metadata for Lead create/edit as pilot. | Changing layout in Studio changes Lead form without redeploy; validation still server-side. | Org User | P0 | 13 | Not Started |  | US-S9-001,US-S4-006
US-S9-003 | S9 | P2 Metadata Studio | List Designer | Studio | List Layout Designer (columns, order, default sort) | Configure default list columns per table; optional role-based default. | Studio UI clutter-free; publish; personalize list can override columns for user. | Org Admin | P0 | 13 | Not Started |  | US-S8-002
US-S9-004 | S9 | P2 Metadata Studio | List Designer | Platform UI | ModuleListShell consumes published list layout | Leads list columns driven by metadata; column chooser persists personal layout. | Admin default applies for new users; personal override saved; export respects visible columns. | Org User | P0 | 8 | Not Started |  | US-S9-003
US-S9-005 | S9 | P2 Metadata Studio | Form Designer | Studio | Declarative form policies (show/hide/mandatory) | If field/condition then set visibility/mandatory/read-only — ServiceNow UI Policy lite. | At least Deal stage→lost reason policy configurable; evaluated client+server; no script editor. | Org Admin | P1 | 13 | Not Started |  | US-S9-002
US-S9-006 | S9 | P2 Metadata Studio | List Designer | RecordShell | Related list layout configuration on RecordShell | Choose which related lists appear and their columns per parent table. | Account related lists configurable; permission-scoped; empty states remain. | Org Admin | P1 | 8 | Not Started |  | US-S6-006,US-S9-003
US-S10-001 | S10 | P2 Metadata Studio | ACL Studio | Security | Table ACL matrix UI (Role × Table × CRUD) | ServiceNow-like checkbox matrix for Create/Read/Update/Delete per role per table. | Org Admin can grant/revoke; changes audited; cannot remove last Org Admin escape hatch. | Org Admin | P0 | 13 | Not Started |  | US-S8-002
US-S10-002 | S10 | P2 Metadata Studio | ACL Studio | Security | Server ACL evaluator enforces table CRUD on all tenant APIs | Central check before service mutate/read; maps to existing permission codes + matrix. | Denied role gets 403 on API; UI hides Create/Edit/Delete; tests for Viewer vs Sales Exec vs Admin. | Engineer | P0 | 13 | Not Started |  | US-S10-001
US-S10-003 | S10 | P2 Metadata Studio | ACL Studio | Roles | User-friendly Roles & Permissions screen redesign | Replace dense permission lists with grouped modules + CRUD summary + link to ACL matrix. | Clutter-free; search permissions; show effective scope; save with confirmation. | Org Admin | P0 | 8 | Not Started |  | US-S10-001
US-S10-004 | S10 | P2 Metadata Studio | ACL Studio | Security | Seed default Table ACLs for all live modules by role | Align ROLE_PERMISSION_MATRIX into ACL seed so out-of-box CRUD matches product intent. | VIEWER read-only; EMPLOYEE limited; ORG_ADMIN full tenant; documented matrix in Studio. | Org Admin | P0 | 8 | Not Started |  | US-S10-001
US-S10-005 | S10 | P2 Metadata Studio | ACL Studio | Navigation | Sidebar module visibility driven by Read ACL + nav config | Hide modules user cannot read; Studio can reorder/hide groups per role. | No dead links; Super Admin platform nav unchanged; tenant nav ACL-aware. | Org User | P1 | 8 | Not Started |  | US-S10-002
US-S11-001 | S11 | P2 Metadata Studio | FLS | Security | Field ACL Studio (Hidden / Read / Write by role) | Configurable FLS beyond hard-coded rates; applies to system + custom fields. | Matrix UI; API strips/hides fields; audit on change. | Org Admin | P0 | 13 | Not Started |  | US-S8-003,US-S10-001
US-S11-002 | S11 | P2 Metadata Studio | FLS | Security | Apply FLS to cost_rate / billing_rate / margin via Field ACL | Replace one-off hard-code with Field ACL seed for finance-sensitive fields. | Sales cannot see rates; Finance can; tests; ready for invoice profitability. | Org Admin | P0 | 8 | Not Started |  | US-S11-001
US-S11-003 | S11 | P2 Metadata Studio | Form Designer | Studio | Publish default form+list layouts for all CRM & delivery modules | Roll DynamicForm + list layouts beyond Leads pilot to Contacts…Timesheets + admin tables. | Each module uses published layout; Studio editable; no regression on Save/Save&New. | Org Admin | P0 | 13 | Not Started |  | US-S9-002,US-S9-004
US-S11-004 | S11 | P2 Metadata Studio | Metadata Studio | Studio | Filter catalog fields sourced from Field Dictionary | Advanced filter whitelists generated from dictionary filterable flags. | New custom field can be marked filterable and appears in filter rail after publish. | Org Admin | P1 | 8 | Not Started |  | US-S8-003,US-S7-001
US-S11-005 | S11 | P2 Metadata Studio | Metadata Studio | Audit Logs | Audit metadata publish and ACL changes | Every Studio publish and ACL edit writes audit with before/after summary. | Filterable in Audit; no secrets; Org Admin can review. | Org Admin | P1 | 5 | Not Started |  | US-S8-001
US-S11-006 | S11 | P2 Metadata Studio | Metadata Studio | Studio | V2 module onboarding rule: register table/fields/layouts/ACLs | Checklist + seed helpers so Invoices/POs/etc always join Studio before UI ship. | Documented DoD; sample registration for a stub module; engineering wiki link in plan. | Tech Lead | P1 | 5 | Not Started |  | US-S11-003,US-S10-004
US-S12-001 | S12 | P3 Depth | CRM Depth | Leads | Bulk assign / bulk status change for Leads | Select rows; bulk actions with permission + audit. | Batch size capped; partial success report; audited; respects Table ACL Update. | Sales Manager | P1 | 8 | Not Started
US-S12-002 | S12 | P3 Depth | CRM Depth | Leads | Duplicate detection warning on Lead create | Warn on matching email/company; allow proceed. | Warning modal; does not block unless configured later. | Sales Exec | P1 | 5 | Not Started
US-S12-003 | S12 | P3 Depth | CRM Depth | Deals | Deal stage conditional fields (close date / lost reason) | Require close date on WON; lost reason on LOST. | Client+server validation; form shows fields conditionally. | Sales Exec | P1 | 5 | Not Started
US-S12-004 | S12 | P3 Depth | CRM Depth | Meetings | Meeting activity richness (attendees, location, outcome) | Extend meeting form/detail without breaking activity model. | Fields optional; list filters by outcome; clutter-free layout. | Sales Exec | P2 | 8 | Not Started
US-S12-005 | S12 | P3 Depth | CRM Depth | Calls | Call activity richness (direction, duration, outcome) | Call-specific fields on activity type CALL. | Create/edit/detail support; filters include direction/outcome. | Sales Exec | P2 | 5 | Not Started
US-S12-006 | S12 | P3 Depth | CRM Depth | Documents | Documents module UX polish + upload from library | Upload attaching to entity from Documents page. | Upload requires entity lookup; list/tile; download works. | Org User | P1 | 5 | Not Started
US-S13-001 | S13 | P3 Depth | Delivery Depth | Projects | Project health indicators on list (on track / delayed) | Derived from dates/milestones without clutter. | Badge on list; filter Delayed works. | PM | P2 | 5 | Not Started
US-S13-002 | S13 | P3 Depth | Delivery Depth | Allocations | Over-allocation warning UX | Surface utilization conflicts clearly on create/edit. | Warning before save; server still enforces rules. | Resource Manager | P1 | 5 | Not Started
US-S13-003 | S13 | P3 Depth | FLS | Security | Regression: rate fields remain protected via Field ACL on delivery screens | Verify Resource/Allocation/Timesheet UIs honor Field ACL from Studio (US-S11-002). | Sales cannot see rates on delivery screens; Finance can; no hard-coded bypass left. | Org Admin | P1 | 5 | Not Started |  | US-S11-002
US-S13-004 | S13 | P3 Depth | CRM Depth | Accounts | Account RecordShell related lists complete | Contacts, Deals, Projects, Activities, Documents, Notes. | All related lists permission-scoped; empty states. | Sales Manager | P1 | 8 | Not Started |  | US-S6-006
US-S14-001 | S14 | P4 Engines | Approval Engine | Approvals | Approval tables + domain model | approval_workflows, steps, requests, actions. | Migrations; entities; no UI yet required. | Engineer | P0 | 8 | Not Started
US-S14-002 | S14 | P4 Engines | Approval Engine | Timesheets | Timesheet approval via Approval Engine (dual-write) | Keep timesheet status in sync with approval_request. | Approve/reject works; history preserved; tests. | PM | P0 | 13 | Not Started |  | US-S14-001
US-S14-003 | S14 | P4 Engines | Approval Engine | Approvals | My Approvals inbox UI | Clutter-free list of pending approvals. | Filter by type; act approve/reject with comment. | Approver | P1 | 8 | Not Started |  | US-S14-001
US-S15-001 | S15 | P4 Engines | Workflow Engine | Workflow | Outbox/domain_events + workflow skeleton | Reliable async actions after commit. | Outbox table; poller; idempotent handler stub. | Engineer | P0 | 13 | Not Started
US-S15-002 | S15 | P4 Engines | Workflow Engine | Deals | Workflow: Deal WON → notify PM (action pack v1) | Typed action NOTIFY; no Deluge. | Event published; notification created; execution audited. | Org Admin | P1 | 8 | Not Started |  | US-S15-001
US-S16-001 | S16 | P5 Finance | Finance | Taxes | Tax rates master (GST-ready) | Tax name/code/rate/jurisdiction; CGST/SGST/IGST capable. | CRUD org-scoped; used on invoice lines. | Finance | P0 | 8 | Not Started
US-S16-002 | S16 | P5 Finance | Finance | Invoices | Invoice schema + draft create from project/account | Invoices, items, numbering sequence. | Draft invoice; org+region; permissions; list shell UX. | Finance | P0 | 13 | Not Started |  | US-S16-001,US-S11-002
US-S16-003 | S16 | P5 Finance | Finance | Invoices | Pull billable approved timesheet lines into invoice | Prevent double billing with unique guard. | Only approved billable; cannot invoice twice; tests. | Finance | P0 | 13 | Not Started |  | US-S16-002
US-S17-001 | S17 | P5 Finance | Finance | Invoices | Invoice lifecycle Issue / Void / Overdue | Immutable issued money fields; void path. | Status transitions validated; audited; UI actions clear. | Finance | P0 | 8 | Not Started |  | US-S16-002
US-S17-002 | S17 | P5 Finance | Finance | Payments | Record payments (partial/full) against invoice | Payment allocation updates balance/status. | Partial→PARTIALLY_PAID; full→PAID; form optimized. | Finance | P0 | 8 | Not Started |  | US-S17-001
US-S17-003 | S17 | P5 Finance | Finance | Invoices | Advanced filters for Invoices | Status, due, overdue, account, balance, date. | FilterEngine catalog; saved views. | Finance | P1 | 5 | Not Started
US-S18-001 | S18 | P5 Finance | Finance | Credit Notes | Credit notes issue/apply | Corrections without editing issued invoices. | Apply reduces balance; audited; permission gated. | Finance | P1 | 13 | Not Started |  | US-S17-001
US-S18-002 | S18 | P5 Finance | Finance | Invoices | Invoice RecordShell + PDF/export later stub | Detail experience for invoice; export CSV first. | Related payments/credits; clutter-free header actions. | Finance | P1 | 8 | Not Started
US-S19-001 | S19 | P6 Contracts/Expenses | Contracts | Contracts | Contracts CRUD + Account/Project link | Value, dates, renewal, terms, status. | ModuleListShell; form sections; org isolation. | Org Admin | P0 | 13 | Not Started
US-S19-002 | S19 | P6 Contracts/Expenses | Contracts | Contracts | Expiry reminders notifications | Scheduler creates notifications N days before end. | Configurable window; no duplicate spam; audited runs. | Org Admin | P1 | 8 | Not Started |  | US-S19-001
US-S19-003 | S19 | P6 Contracts/Expenses | Contracts | Contracts | Advanced filters for Contracts | Status, expiry window, account, auto-renew. | Relative date expiry filters work. | Org Admin | P1 | 5 | Not Started
US-S20-001 | S20 | P6 Contracts/Expenses | Expenses | Expenses | Expenses CRUD with receipt documents | Employee/project expenses; categories; billable flag. | Upload receipt via Documents; form optimized; list filters. | Employee | P0 | 13 | Not Started
US-S20-002 | S20 | P6 Contracts/Expenses | Expenses | Expenses | Expense approval via Approval Engine | Submit → approve/reject. | Appears in My Approvals; status synced. | PM/Finance | P0 | 8 | Not Started |  | US-S14-001,US-S20-001
US-S20-003 | S20 | P6 Contracts/Expenses | Expenses | Expenses | Advanced filters for Expenses | Category, project, employee, approval status, billable. | Catalog complete; saved views. | Finance | P1 | 5 | Not Started
US-S21-001 | S21 | P7 Procurement | Procurement | Vendors | Vendors module CRUD | Vendor master for procurement. | List/form/detail; filters; org isolation. | Finance | P0 | 8 | Not Started
US-S21-002 | S21 | P7 Procurement | Procurement | Purchase Orders | Purchase Orders + PO items draft | PO linked to vendor/project. | Create draft with lines; totals; ModuleListShell UX. | Finance | P0 | 13 | Not Started |  | US-S21-001
US-S22-001 | S22 | P7 Procurement | Procurement | Purchase Orders | PO approval + status lifecycle | PENDING_APPROVAL → APPROVED/REJECTED → SENT/CLOSED. | Uses Approval Engine; audited. | Org Admin | P0 | 13 | Not Started |  | US-S14-001,US-S21-002
US-S22-002 | S22 | P7 Procurement | Procurement | Purchase Orders | Advanced filters for POs and Vendors | Status, vendor, project, amount, approval state. | Filter catalogs live. | Finance | P1 | 5 | Not Started
US-S23-001 | S23 | P8 Reports | Reports | Reports | Reports module shell + permission REPORT_VIEW | Clutter-free report gallery. | Nav enabled; cards for available reports only. | Org Admin | P0 | 5 | Not Started
US-S23-002 | S23 | P8 Reports | Reports | Reports | Sales & pipeline analytics report | Lead funnel, win/loss, pipeline by stage. | Filters region/date; export CSV; org scoped. | Sales Manager | P0 | 13 | Not Started
US-S23-003 | S23 | P8 Reports | Reports | Reports | Project & timesheet analytics report | Status, hours billable/non-billable, delays. | Filters project/date; permissioned. | PM | P1 | 8 | Not Started
US-S24-001 | S24 | P8 Reports | Reports | Reports | Finance AR & invoice aging report | Outstanding, aging buckets. | Respects FLS; Finance permission. | Finance | P0 | 8 | Not Started |  | US-S17-002
US-S24-002 | S24 | P8 Reports | Reports | Reports | Project profitability report | Revenue − resource cost − expenses. | RATE_VIEW for cost; formula documented; export. | Org Admin | P0 | 13 | Not Started |  | US-S11-002,US-S16-002,US-S20-001
US-S24-003 | S24 | P8 Reports | Reports | Reports | Advanced filters on all report pages | Date range, region, owner, account, project. | Consistent filter UX; no clutter. | Org User | P1 | 5 | Not Started
US-S25-001 | S25 | P9 Portal | Customer Portal | Portal | portal_users + portal auth audience | Separate auth; never mix with internal users. | Login/refresh; JWT audience PORTAL; isolation tests. | Customer User | P0 | 13 | Not Started
US-S25-002 | S25 | P9 Portal | Customer Portal | Portal | Portal read APIs for projects/invoices/documents | Account-scoped only; no costs/margins/audit. | IDOR tests; visibility=CUSTOMER documents only. | Customer User | P0 | 13 | Not Started |  | US-S25-001
US-S26-001 | S26 | P9 Portal | Customer Portal | Portal | Portal UI (clutter-free customer experience) | /portal routes; limited nav. | Projects, invoices, docs; no admin chrome. | Customer User | P0 | 13 | Not Started |  | US-S25-002
US-S26-002 | S26 | P9 Portal | Hardening | Platform | V2 production hardening checklist | Swagger off, rate limits, backups, seed cleanup, perf smoke. | Checklist signed; CRITICAL bugs zero. | Tech Lead | P0 | 8 | Not Started
US-S26-003 | S26 | P9 Portal | Hardening | All | End-to-end UAT: Platform sell → Org CRM → Invoice → Portal | Golden path across Super Admin and tenant. | UAT script pass; Excel stories for path marked Done. | Product Owner | P0 | 8 | Not Started
US-CX-001 | S4 | P1 UX System | UX Quality | All | Empty/Loading/Error/Forbidden states audit all modules | Every list/detail has consistent states. | Checklist per module; no blank white failures. | QA | P1 | 5 | Not Started
US-CX-002 | S7 | P1 UX System | Advanced Filters | All | Saved Views shared/public (org admin) | Extend private views to SHARED/PUBLIC with ACL. | Only Org Admin publishes PUBLIC; others private/shared. | Org Admin | P2 | 8 | Not Started
US-CX-003 | S1 | P0 Platform Split | Documentation | Docs | Update ROLE_PERMISSION_MATRIX for Platform vs Tenant | Document Super Admin cannot use tenant Leads. | Matrix updated; linked from plan. | Product Owner | P1 | 2 | Done |  |  | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S5-008 | S5 | P1 UX System | Form System | Timesheets | Timesheet submit/approve UI polish (clutter-free) | Clear week grid actions; approval comments; status badges. | Employee and approver flows obvious; errors inline. | Employee/PM | P1 | 5 | Not Started
US-S6-008 | S6 | P1 UX System | Form System | Settings | Organization settings form (currency, timezone, tax defaults) | Tenant settings page optimized; Super Admin does not edit tenant settings here. | Org Admin only; validation; audited updates. | Org Admin | P1 | 5 | Not Started
US-S12-007 | S12 | P3 Depth | CRM Depth | Tasks | Activity Task manage (complete, reschedule, priority) | Full manage actions inside Tasks list/detail. | Complete/reschedule from detail; filters overdue/today. | Sales Exec | P1 | 5 | Not Started
US-S12-008 | S12 | P3 Depth | CRM Depth | Meetings | Manage meetings (reschedule, complete, related record) | Meeting lifecycle from list and RecordShell. | Actions permissioned; related entity required. | Sales Exec | P1 | 5 | Not Started
US-S12-009 | S12 | P3 Depth | CRM Depth | Calls | Manage calls (log outcome, complete) | Call logging optimized for speed. | Quick log form; outcome required on complete. | Sales Exec | P1 | 5 | Not Started
US-S2-005 | S2 | P0 Platform Split | Organizations | Organizations | Seed default roles/permissions when creating organization | New org gets system roles catalog copy/grants. | Org Admin can login and manage users; isolation verified. | Super Admin | P0 | 8 | Done |  | US-S2-002 | 2026-09-22 | Shipped Sprint 1-2 Platform Console + Orgs
US-S13-005 | S13 | P3 Depth | Delivery Depth | Skills | Skill matrix UX on Resource detail | Assign proficiency levels clutter-free. | Add/remove skills; filters by skill on Resources. | Resource Manager | P2 | 5 | Not Started
US-S15-003 | S15 | P4 Engines | Workflow Engine | Workflow | Workflow admin UI (definitions list — read/configure basic) | Minimal UI to enable/disable workflow definitions. | Org Admin can toggle; no script injection; audited. | Org Admin | P2 | 8 | Not Started |  | US-S15-001
US-S18-003 | S18 | P5 Finance | Finance | Finance | Finance nav module group + permission seeding | Enable Invoices/Payments nav by permission after seed. | Hidden without permission; Super Admin platform nav separate. | Finance | P0 | 3 | Not Started
US-S23-004 | S23 | P8 Reports | Reports | Reports | Resource utilization report | Capacity vs allocated vs timesheet hours. | Date/region filters; RATE fields FLS safe. | Resource Manager | P1 | 8 | Not Started |  | US-S11-002
US-S24-004 | S24 | P8 Reports | Reports | Reports | Procurement & expense spend reports | PO spend by vendor/project; expenses by category. | Exports; org scoped. | Finance | P1 | 8 | Not Started |  | US-S20-001,US-S21-002
US-S3-005 | S3 | P0 Platform Split | Prospect Orgs | Prospect Orgs | Prospect Org notes/documents (platform) | Attach proposals while selling TechEarnest. | Notes+docs on prospect; platform-only storage scope. | Super Admin | P2 | 5 | Not Started |  | US-S3-001
US-CX-004 | S7 | P1 UX System | UX Quality | All | Accessibility pass (keyboard, focus, labels) on ModuleListShell | High-level UI remains usable via keyboard. | Filter toggle, table, create reachable; contrast OK. | QA | P2 | 5 | Not Started
US-CX-005 | S26 | P9 Portal | Hardening | Security | Cross-tenant isolation regression suite for all V2 modules | Automated tests org A cannot see org B finance/CRM. | Suite green in CI; covers invoices/expenses/contracts/POs. | Tech Lead | P0 | 13 | Not Started

## Legend
Status | Meaning
Not Started | Queued
In Progress | Actively being built
Blocked | Waiting on dependency/decision
Done | Meets Definition of Done
Deferred | Moved out of current release intentionally
Priority | Meaning
P0 | Must for phase gate
P1 | Should in phase
P2 | Nice / deepen
P3 | Future

## Epics
Epic | Stories | Points
Platform Console | 5 | 24
Organizations | 5 | 36
Prospect Orgs | 4 | 31
Form System | 20 | 103
RecordShell | 2 | 18
Advanced Filters | 14 | 73
Metadata Studio | 8 | 70
Form Designer | 4 | 52
List Designer | 3 | 29
ACL Studio | 5 | 50
FLS | 3 | 26
CRM Depth | 10 | 59
Delivery Depth | 3 | 15
Approval Engine | 3 | 29
Workflow Engine | 3 | 29
Finance | 9 | 79
Contracts | 3 | 26
Expenses | 3 | 26
Procurement | 4 | 39
Reports | 8 | 68
Customer Portal | 3 | 39
Hardening | 3 | 29
UX Quality | 2 | 10
Documentation | 1 | 2